## Read me first (SOP)
Thruster Package Register — How to handle incoming submissions
Non-technical intake guide for the admin / shared-mailbox team. Keep this workbook on the shared drive so everyone updates the same file.
THE GOLDEN RULE
One thruster = ONE BV project registration = ONE review package — no matter how many separate deliveries (tranches) of drawings arrive over the months. Everything for that thruster is keyed to the CLIENT PO NUMBER (plus vessel/hull and thruster tag). You never need to understand the drawings — you only need to match the PO number.
WHY THIS MATTERS
Thruster drawings do not all arrive at once. A typical thruster is delivered in tranches over ~6 months: Mechanical / structural first, then Hydraulic, then Electrical / Control, and the Torsional Vibration (TVC) usually LAST. If a later tranche is opened as a NEW package, one thruster ends up split across several packages — which is wrong. This workbook stops that.
STEP-BY-STEP — every time a submission email arrives
1. Open the 'Intake Log' sheet. Add a new row.
2. Enter today's Date and the Client PO number (read it from the email / subject / cover letter).
3. Look at the 'ACTION' column — it fills in automatically:
✓ EXISTING → route to BV-Reg-XXX = this PO is already registered. Do NOT create a new package.
➤ NEW PACKAGE — create BV registration = this PO has never been seen before.
4. If EXISTING: forward the drawings to the review team under the BV Reg No shown, then go to 'Package Register',
find that row, and fill in the received-date for the discipline that just arrived (Mechanical / Hydraulic / etc.).
5. If NEW: create the BV project registration number as usual, add ONE row to 'Package Register',
then send the client the acknowledgement email (template below) so they quote the BV Reg No on all future tranches.
6. Never open a second registration for the same PO / vessel / thruster tag.
IF THE CLIENT DID NOT QUOTE THE PO NUMBER
Search the 'Package Register' (Ctrl+F) by Vessel / Hull number, Client name, or Thruster tag to find the existing registration. Still unsure which package it belongs to? Flag it to the responsible plan-approval surveyor before creating anything — do not guess by opening a new package.
WHEN IS A PACKAGE COMPLETE?
In 'Package Register', the 'Still outstanding' column lists the disciplines not yet received. When it is empty, all expected tranches (including the TVC) are in. The surveyor marks 'N/A' for any discipline a given thruster does not need (e.g. no hydraulics on a simple fixed-pitch electric tunnel thruster) — use the interactive Quick-Reference tool to see which disciplines that thruster type requires.
ACKNOWLEDGEMENT EMAIL TEMPLATE (send on first receipt of a NEW package)
Subject: BV Project Registration [BV-Reg-No] — Thruster [tag], Vessel [name/hull], PO [PO no] Dear [Client], We confirm receipt of your submission under Purchase Order [PO no]. This thruster has been registered under Bureau Veritas Project Registration No. [BV-Reg-No]. Please quote this BV Registration Number — together with the PO number and thruster tag [tag] — on ALL future submissions for this thruster, including the later hydraulic, electrical/control and torsional-vibration (TVC) drawings. This ensures every delivery is added to the same review package. Kind regards, [Name] — Bureau Veritas Marine & Offshore, Plan Approval
Tip: keeping the client disciplined about quoting the BV Reg No is the single most effective fix — it removes the guesswork entirely.

## Package Register
BV Reg No | Client PO No | Client / Yard | Vessel / Hull No | Thruster tag(s) & qty | Thruster type | Prime mover | Date opened | Mechanical rcvd | Hydraulic rcvd | Electrical rcvd | Control rcvd | TVC rcvd | Testing/other rcvd | Still outstanding | Status | Last update | Notes
BV-THR-2026-001 | PO-88123 | Damen / Yard 512 | MV Northern Star / H-512 | AZ-1 & AZ-2 (2 off) | Azimuth (rotating) | Diesel | 2026-01-15 | 2026-01-15 | 2026-03-02 | [5 empty] | Open - awaiting drawings | 2026-03-02 | EXAMPLE ROW — delete. Awaiting Electrical, Control, TVC.

## Intake Log
Date received | Client PO No | BV Reg No (auto) | ACTION (auto) | Vessel/Hull (auto) | Thruster tag (auto) | Sender / email | Drawings received (titles / count) | Discipline | Tranche # | Routed to | Notes
2026-01-15 | PO-88123 |  |  |  |  | engineering@damen.example | GA + propeller + shaft (5 dwgs) | Mechanical | 1 | Machinery reviewer
2026-03-02 | PO-88123 |  |  |  |  | engineering@damen.example | HPU + hydraulic schematic (3 dwgs) | Hydraulic | 2 | Machinery reviewer

## Lists (hidden)
Thruster type | Prime mover | Discipline | Status | Yes/No/NA
Tunnel (transverse) | Electric | General/Admin | Open - awaiting drawings | Yes
Retractable tunnel | Diesel | Structural | In review | No
Azimuth (rotating) | Hydraulic | Mechanical | Complete - all received | N/A
Retractable azimuth |  | Hydraulic | On hold
Azimuth CP |  | Electrical | Closed
Podded |  | Control
Water-jet |  | Torsional Vibration (TVC)
Voith-Schneider |  | Testing
Rim-driven |  | Other
Pump-jet
Gill/hydro-jet
Steering grid/nozzle
Other